TripWise AI – Intelligent Travel Planning System

Development Roadmap and Implementation Strategy

| Project Name: | TripWise AI – Intelligent Travel Planning System |
| --- | --- |
| Document Type: | Development Roadmap and Implementation Strategy |
| Planning Duration: | 12 Weeks |
| Development Approach: | Agile Methodology with Iterative Development |
| Document Purpose: | To establish a structured development schedule, implementation approach, resource estimates, testing strategy, and risk mitigation plan for TripWise AI. |

1. Introduction

Software development requires systematic planning to ensure that project objectives are achieved within the available time, resources, and technical constraints. A clearly defined development roadmap helps a development team organize tasks, assign responsibilities, monitor progress, and identify potential problems before they affect the final product.

TripWise AI is an intelligent travel planning web application designed to simplify the process of organizing trips. The proposed system aims to help users explore destinations, estimate travel expenses, compare transportation options, and identify suitable accommodation and places to visit. The system is intended to provide a convenient and structured travel planning experience based on user preferences, travel dates, and budget.

2. Project Objectives

Divide the development process into logical and manageable stages.

Define milestones, deliverables, and completion criteria for each stage.

Select an appropriate development methodology.

Estimate the time and effort required for implementation.

Establish a clear strategy for coding, version control, and module integration.

Develop a comprehensive testing and quality assurance plan.

Identify potential technical, scheduling, and operational risks.

Define mitigation strategies to reduce project delays and failures.

Prepare the application for deployment and future enhancement.

Maintain clear technical documentation throughout the development lifecycle.

3. Project Scope

3.1 Minimum Viable Product (MVP)

Trip Input Interface: Form for destination, dates, travellers, and budget.

Destination Recommendation Module: Suggests destinations based on user preferences.

Budget Estimation Module: Estimates transportation, accommodation, food, and activity costs.

Transportation Comparison Module: Compares route options and travel details.

Accommodation and Places Module: Recommends stays and attractions.

Trip Plan Display: Organized view of travel itinerary.

Error Handling: Form validation and fallback handling.

Responsive UI: Adapts to desktop and mobile screens.

3.2 Features Outside Initial Scope

Direct booking / ticket purchase.

Online payment gateway integration.

Advanced ML personalization.

Native mobile applications (iOS/Android).

4. Development Methodology & Agile Cycle

The Agile methodology is selected for TripWise AI because it supports incremental development, regular feedback, and continuous improvement. The proposed development cycle consists of seven key sprint steps:

| Phase | Sprint Step | Key Activities & Focus | Next Step |
| --- | --- | --- | --- |
| 01 | 1. Planning | Define sprint goals, prioritize backlog items, and assign team tasks. | → Step 2 |
| 02 | 2. Requirement Analysis | Refine feature specifications, user stories, and technical criteria. | → Step 3 |
| 03 | 3. Design | Create UI/UX wireframes, architecture updates, and API contracts. | → Step 4 |
| 04 | 4. Implementation | Develop core frontend components, backend endpoints, and data models. | → Step 5 |
| 05 | 5. Testing | Execute unit tests, integration verification, and bug fixing. | → Step 6 |
| 06 | 6. Review | Demonstrate working features to stakeholders and gather feedback. | → Step 7 |
| 07 | 7. Retrospective | Analyze process performance and optimize upcoming sprint workflow. | ↺ Loop (Step 1) |

5. 12-Week Development Roadmap

| Timeline | Milestone | Core Deliverables & Focus Area |
| --- | --- | --- |
| Weeks 01–02 | [M1–M2] | Planning & Design Baseline: System Architecture, User Wireframes & API Data Contracts. |
| Week 03 | [M3] | Project Foundation: Repository Setup, Skeleton Application & Dev Environment. |
| Weeks 04–05 | [M4] | Core Workflow: End-to-End Trip Input Form to Plan Display Integration. |
| Weeks 06–07 | [M5] | Business Logic: Destination Recommendation Engine & Budget Calculation Module. |
| Week 08 | [M6] | Adapters Integration: Transport & Places External API Adapters with Fallbacks. |
| Week 09 | [M7] | Full Integration: Connected Application Modules & Contract Testing Execution. |
| Weeks 10–11 | [M8] | Quality Assurance: System Testing, UI Polish & Release Candidate Validation. |
| Week 12 | [M9] | Deployment: Production Deployment, Documentation & System Handover. |

6. Milestone Summary Table

| Milestone | Target | Evidence of Completion |
| --- | --- | --- |
| M1: Scope Baseline | End of Week 1 | Requirements, MVP scope, acceptance criteria |
| M2: Design Baseline | End of Week 2 | Architecture, wireframes, API & data contracts |
| M3: Project Foundation | End of Week 3 | Repository, runnable skeleton, setup instructions |
| M4: First E2E Workflow | End of Week 5 | Trip input to plan display demonstration |
| M5: Core Business Features | End of Week 7 | Recommendation & budget test results |
| M6: Integration Readiness | End of Week 8 | Transport & places flows with fallback handling |
| M7: Integrated App | End of Week 9 | Integration test results and connected modules |
| M8: Release Candidate | End of Week 11 | System test report and defect status |
| M9: Deployment & Handover | End of Week 12 | Smoke-test results and handover documents |

7. System Architecture & Module Data Flow

The TripWise AI platform is built upon a 3-tier modular architecture designed for high maintainability, fault tolerance, and clear boundary separation:

| Architecture Layer | Components & Responsibilities | Communication & Protocols |
| --- | --- | --- |
| Frontend Presentation Layer | React Single Page Application (SPA) • UI Form Inputs (Destination, Dates, Travelers, Budget) • Interactive Trip Plan & Itinerary Display Cards • Client-side Input Validation & Responsive Layouts | HTTPS / REST API (JSON Payloads) |
| Backend & Core Business Logic Layer | Node.js / Express Server • Budget Calculation Engine (Transportation, Stay, Food & Activities) • Recommendation Engine & Destination Ranking Logic • Request Routing, Middleware & Error Handling | REST Endpoints / SQL & External API Adapters |
| Data & External Services Layer | Database & External Provider Adapters • PostgreSQL Database (User Data, Trip Records, Cached Information) • Transportation & Route External Services (API Adapters & Fallbacks) • Accommodation & Places Recommendation Providers | SQL Queries / External REST APIs |

8. Resource and Effort Allocation

| Activity / Work Package | Estimated Hours |
| --- | --- |
| Requirements & Planning | 12 hrs |
| Architecture & Design | 18 hrs |
| Repository Setup | 10 hrs |
| Core Trip Planning Workflow | 28 hrs |
| Recommendation & Budget Features | 26 hrs |
| Transportation & Places Integration | 16 hrs |
| Module Integration | 16 hrs |
| System Testing & Refinement | 28 hrs |
| Deployment & Handover | 12 hrs |
| Contingency Reserve | 25 hrs |
| Total Effort | 191 Person-Hours (~16 hrs/week) |

9. Risk Assessment and Mitigation Matrix

| Risk Factor | Probability / Impact | Mitigation Strategy |
| --- | --- | --- |
| External API downtime / rate limits | Medium / High | Use adapters, timeouts, controlled sample data, and fallback handling. |
| Inaccurate travel cost estimates | Medium / High | Label estimates as approximate, document cost assumptions clearly. |
| Scope expansion | High / High | Establish MVP scope early, move non-essential features to future backlogs. |
| Integration delays | Medium / High | Freeze API contracts by Week 2; test full workflow by Week 5. |
| Exposure of secrets / API keys | Low / High | Exclude secrets from Git, utilize .env templates securely. |

10. Conclusion and References

This document establishes a structured, Agile-driven 12-week roadmap for developing TripWise AI into a functional, reliable Minimum Viable Product.

References

Schwaber, K., & Sutherland, J. (2020). The Scrum Guide.

Agile Alliance. Principles behind the Agile Manifesto.

OWASP Foundation. Application Security Verification Standard.

Vercel. Next.js Documentation.

OpenJS Foundation. Express Documentation.